## Overview
AI Agent Engineer - 8-Week Learning Plan
Profile: 6-year Java + Vue full-stack developer ¦ Stack: Python + React ¦ Final Project: Security Analyst Agent
Week | Theme | Goal | Primary Resources | Planned Hours | Completed Tasks | Total Tasks | Progress
1 | Agent Foundations | 理解 Agent、Workflow、Context、Tool Design；完成第一个 Tool Agent | Anthropic + OpenAI Agents SDK | 19 | 0 | 7 | 0%
2 | Claude API + Agent Development | 掌握 Claude API、Streaming、Structured Output 与 Tool Use | Claude Academy | 19 | 0 | 7 | 0%
3 | MCP | 理解 MCP Host/Client/Server，并开发 GitHub MCP Server | Hugging Face MCP Course | 19 | 0 | 7 | 0%
4 | OpenAI Agents SDK | 掌握 Agent、Guardrail、Session、Tracing、Handoff | OpenAI Agents SDK | 19 | 0 | 7 | 0%
5 | RAG + Knowledge Base | 构建基于 Qdrant 的企业知识库 Agent | Qdrant | 19 | 0 | 7 | 0%
6 | LangGraph | 掌握状态图、条件路由、Checkpoint 与 HITL | LangGraph | 19 | 0 | 7 | 0%
7 | React Agent UI | 使用 React/Next.js 构建流式 Agent UI | React + Next.js + Vercel AI SDK | 19 | 0 | 7 | 0%
8 | Security Analyst Agent | 整合 CVE、ATT&CK、IOC、报告生成与多 Agent | MITRE ATT&CK + NVD | 20 | 0 | 7 | 0%
Overall KPI | Value
Total Tasks | 56
Completed Tasks | 0
Planned Hours | 153
Overall Progress | 0%

## Plan
Week | Day | Topic | Learning Tasks | Deliverable | Resource | Source URL | Hours | Status | Notes
1 | 1 | Workflow vs Agent | 阅读 Building Effective Agents；理解 Workflow、Agent 及适用边界 | agent-fundamentals.md | Anthropic Building Effective Agents | https://www.anthropic.com/research/building-effective-agents | 2 | 未开始
1 | 2 | Context Engineering | 学习 Context Window、Short-Term Memory、Long-Term Memory | context-engineering.md | Anthropic Engineering | https://www.anthropic.com/engineering | 2 | 未开始
1 | 3 | Tool Design | 学习 Tool Schema、输入输出边界、错误处理 | tools-design.md | Anthropic Engineering | https://www.anthropic.com/engineering | 2 | 未开始
1 | 4 | SDK Quick Start | 配置 Python 环境；安装 OpenAI Agents SDK；运行 Quick Start | hello-agent.py | OpenAI Agents SDK Docs | https://openai.github.io/openai-agents-python/ | 2 | 未开始
1 | 5 | Calculator Agent | 开发 Calculator Tool 与 Date Tool | calculator-agent.py | OpenAI Agents SDK Docs | https://openai.github.io/openai-agents-python/ | 2 | 未开始
1 | 6 | Multi-Tool Agent | 开发 Weather Mock Tool；组合多个工具 | weather-agent.py | OpenAI Agents SDK Docs | https://openai.github.io/openai-agents-python/ | 5 | 未开始
1 | 7 | 周复盘 | 整理知识体系；绘制 Agent Architecture Diagram | Week1-Review.md | Anthropic Building Effective Agents | https://www.anthropic.com/research/building-effective-agents | 4 | 未开始
2 | 8 | Claude Platform 101 | 学习 Messages API、模型调用与基础参数 | claude-api-notes.md | Claude Academy | https://academy.claude.com/collections/build-with-claude | 2 | 未开始
2 | 9 | Streaming & Context | 实现流式响应；练习 Context Management | streaming-demo.py | Claude Academy | https://academy.claude.com/collections/build-with-claude | 2 | 未开始
2 | 10 | API Fundamentals | 完成 Claude API 基础课程与示例 | api-fundamentals.py | Claude Academy | https://academy.claude.com/collections/build-with-claude | 2 | 未开始
2 | 11 | Prompt & Structured Output | 练习 Prompt Engineering 与结构化输出 | structured-output.py | Claude Academy | https://academy.claude.com/collections/build-with-claude | 2 | 未开始
2 | 12 | Tool Use | 实现 Tool Calling；优化工具描述与参数模型 | tool-use-demo.py | Claude Academy | https://academy.claude.com/collections/build-with-claude | 2 | 未开始
2 | 13 | Research Agent | 实现搜索、总结、引用的数据流 | research-agent-v0.1 | Claude Academy | https://academy.claude.com/collections/build-with-claude | 5 | 未开始
2 | 14 | 周项目验收 | 补充异常处理、README 与测试用例 | Research Agent v1 | Claude Academy | https://academy.claude.com/collections/build-with-claude | 4 | 未开始
3 | 15 | MCP Overview | 学习 MCP 目标、核心概念与使用场景 | mcp-overview.md | Hugging Face MCP Course | https://huggingface.co/learn/mcp-course/unit0/introduction | 2 | 未开始
3 | 16 | MCP Architecture | 理解 Host、Client、Server、Tool、Resource、Prompt | mcp-architecture.md | Hugging Face MCP Course | https://huggingface.co/learn/mcp-course/unit0/introduction | 2 | 未开始
3 | 17 | Python MCP SDK | 完成 Python SDK 教程与基础示例 | mcp-sdk-demo.py | Hugging Face MCP Course | https://huggingface.co/learn/mcp-course/unit0/introduction | 2 | 未开始
3 | 18 | Hello MCP Server | 开发并测试第一个 MCP Server | hello-mcp-server | Hugging Face MCP Course | https://huggingface.co/learn/mcp-course/unit0/introduction | 2 | 未开始
3 | 19 | File MCP Server | 实现受控 Read File 与 Write File 工具 | file-mcp-server | Hugging Face MCP Course | https://huggingface.co/learn/mcp-course/unit0/introduction | 2 | 未开始
3 | 20 | GitHub MCP Server | 实现 Repository、PR、Issue 查询 | github-mcp-server | Hugging Face MCP Course | https://huggingface.co/learn/mcp-course/unit0/introduction | 5 | 未开始
3 | 21 | 周复盘 | 绘制 Agent + MCP 架构图；整理安全边界 | Week3-Review.md | Hugging Face MCP Course | https://huggingface.co/learn/mcp-course/unit0/introduction | 4 | 未开始
4 | 22 | Agent & Instructions | 掌握 Agent 定义、Instructions 与 Tool 注册 | agent-basics.py | OpenAI Agents SDK Docs | https://openai.github.io/openai-agents-python/ | 2 | 未开始
4 | 23 | Guardrails | 实现输入与输出 Guardrail | guardrails.py | OpenAI Agents SDK Docs | https://openai.github.io/openai-agents-python/ | 2 | 未开始
4 | 24 | Sessions & Memory | 掌握 Session 状态和对话记忆 | sessions-memory.py | OpenAI Agents SDK Docs | https://openai.github.io/openai-agents-python/ | 2 | 未开始
4 | 25 | Tracing | 启用 Tracing；分析一次完整调用链 | tracing-notes.md | OpenAI Agents SDK Docs | https://openai.github.io/openai-agents-python/ | 2 | 未开始
4 | 26 | Handoffs | 实现 Agent 间 Handoff 与责任边界 | handoffs.py | OpenAI Agents SDK Docs | https://openai.github.io/openai-agents-python/ | 2 | 未开始
4 | 27 | Security Research Agent | 实现安全研究单 Agent，加入结构化报告 | security-research-agent | OpenAI Agents SDK Docs | https://openai.github.io/openai-agents-python/ | 5 | 未开始
4 | 28 | Mini Deep Research | 实现 Planner/Researcher/Writer 协作与引用 | mini-deep-research | OpenAI Agents SDK GitHub | https://github.com/openai/openai-agents-python | 4 | 未开始
5 | 29 | Vector DB & Embedding | 理解 Collection、Point、Vector、Embedding | qdrant-basics.md | Qdrant Documentation | https://qdrant.tech/documentation/ | 2 | 未开始
5 | 30 | Chunking Strategy | 比较固定长度、递归与语义分块 | chunking-experiment.md | Qdrant Documentation | https://qdrant.tech/documentation/ | 2 | 未开始
5 | 31 | Retrieval Strategy | 实现 Top-K、Metadata Filter 与 Hybrid Search | retrieval-demo.py | Qdrant Documentation | https://qdrant.tech/documentation/ | 2 | 未开始
5 | 32 | PDF Parser | 解析 PDF；保留页码与来源元数据 | pdf-parser.py | Qdrant Documentation | https://qdrant.tech/documentation/ | 2 | 未开始
5 | 33 | Document Indexer | 实现文档切分、Embedding 与索引 | document-indexer.py | Qdrant Documentation | https://qdrant.tech/documentation/ | 2 | 未开始
5 | 34 | RAG Agent | 实现检索、回答及来源引用 | rag-agent | Qdrant Documentation | https://qdrant.tech/documentation/ | 5 | 未开始
5 | 35 | Knowledge Agent V1 | 完成测试集、README 与演示 | knowledge-agent-v1 | Qdrant Documentation | https://qdrant.tech/documentation/ | 4 | 未开始
6 | 36 | State, Node, Edge | 掌握核心抽象并完成最小示例 | langgraph-notes.md | LangGraph Documentation | https://docs.langchain.com/oss/python/langgraph/overview | 2 | 未开始
6 | 37 | First Graph | 构建第一个状态图 | first-graph.py | LangGraph Documentation | https://docs.langchain.com/oss/python/langgraph/overview | 2 | 未开始
6 | 38 | Conditional Routing | 基于状态实现条件分支与回退 | conditional-routing.py | LangGraph Documentation | https://docs.langchain.com/oss/python/langgraph/overview | 2 | 未开始
6 | 39 | State Management | 设计 Typed State 与状态更新规则 | state-management.py | LangGraph Documentation | https://docs.langchain.com/oss/python/langgraph/overview | 2 | 未开始
6 | 40 | Checkpoint | 实现持久化与中断恢复 | checkpoint-demo.py | LangGraph Documentation | https://docs.langchain.com/oss/python/langgraph/overview | 2 | 未开始
6 | 41 | Human-in-the-Loop | 实现人工审批、修改与继续执行 | hitl-demo.py | LangGraph Documentation | https://docs.langchain.com/oss/python/langgraph/overview | 5 | 未开始
6 | 42 | Document Review Agent | 构建文档审查工作流并完成验收 | document-review-agent | LangGraph Documentation | https://docs.langchain.com/oss/python/langgraph/overview | 4 | 未开始
7 | 43 | React Refresh | 复习 Components、Props、Hooks、State | react-practice | React Learn | https://react.dev/learn | 2 | 未开始
7 | 44 | Context & Custom Hooks | 实现会话状态与可复用 Hook | agent-hooks.ts | React Learn | https://react.dev/learn | 2 | 未开始
7 | 45 | Next.js App Router | 掌握 Routing、Server/Client Components | nextjs-shell | Next.js Learn | https://nextjs.org/learn | 2 | 未开始
7 | 46 | SSE Streaming | 实现 FastAPI 到 React 的流式传输 | sse-demo | Vercel AI SDK | https://sdk.vercel.ai/docs | 2 | 未开始
7 | 47 | Chat UI | 实现消息列表、输入框、Markdown 与引用 | chat-ui | Vercel AI SDK | https://sdk.vercel.ai/docs | 2 | 未开始
7 | 48 | Tool Status Panel | 展示工具调用、状态、耗时与错误 | tool-status-panel | Vercel AI SDK | https://sdk.vercel.ai/docs | 5 | 未开始
7 | 49 | Agent Frontend V1 | 完成联调、错误态、空态与响应式布局 | agent-frontend-v1 | Next.js Learn | https://nextjs.org/learn | 4 | 未开始
8 | 50 | 项目初始化 | 初始化 FastAPI、Next.js、PostgreSQL、Qdrant 与 Docker Compose | security-agent-repo | OpenAI Agents SDK Docs | https://openai.github.io/openai-agents-python/ | 2 | 未开始
8 | 51 | 数据准备 | 接入 CVE 与 ATT&CK 数据；设计字段和更新策略 | security-data-pipeline | MITRE ATT&CK | https://attack.mitre.org/ | 2 | 未开始
8 | 52 | CVE Analyzer Agent | 实现 CVE 摘要、影响分析与证据引用 | cve-analyzer-agent | NVD | https://nvd.nist.gov/ | 2 | 未开始
8 | 53 | ATT&CK Mapper Agent | 将安全描述映射到 ATT&CK 技术并保留依据 | attack-mapper-agent | MITRE ATT&CK | https://attack.mitre.org/ | 2 | 未开始
8 | 54 | IOC Extractor Agent | 提取 IP、Domain、URL、Hash 并结构化输出 | ioc-extractor-agent | OpenAI Agents SDK Docs | https://openai.github.io/openai-agents-python/ | 2 | 未开始
8 | 55 | Report Writer Agent | 生成结构化安全分析报告并整合引用 | report-writer-agent | OpenAI Agents SDK Docs | https://openai.github.io/openai-agents-python/ | 5 | 未开始
8 | 56 | 最终验收 | 串联 Multi-Agent Workflow；前后端联调；Docker 部署；README；Demo | Security Analyst Agent v1 | LangGraph Documentation | https://docs.langchain.com/oss/python/langgraph/overview | 5 | 未开始

## Weekly Checklist
Week | Weekly Goal | Weekly Deliverable | Review Checklist | Status | Review Notes
Week 1 - Agent Foundations | 理解 Agent、Workflow、Context、Tool Design；完成第一个 Tool Agent | Tool Agent + Architecture Notes | □ Code runs □ README updated □ Key concepts summarized □ Demo completed | 未开始
Week 2 - Claude API + Agent Development | 掌握 Claude API、Streaming、Structured Output 与 Tool Use | Research Agent v1 | □ Code runs □ README updated □ Key concepts summarized □ Demo completed | 未开始
Week 3 - MCP | 理解 MCP Host/Client/Server，并开发 GitHub MCP Server | GitHub MCP Server + Architecture | □ Code runs □ README updated □ Key concepts summarized □ Demo completed | 未开始
Week 4 - OpenAI Agents SDK | 掌握 Agent、Guardrail、Session、Tracing、Handoff | Mini Deep Research | □ Code runs □ README updated □ Key concepts summarized □ Demo completed | 未开始
Week 5 - RAG + Knowledge Base | 构建基于 Qdrant 的企业知识库 Agent | Knowledge Agent v1 | □ Code runs □ README updated □ Key concepts summarized □ Demo completed | 未开始
Week 6 - LangGraph | 掌握状态图、条件路由、Checkpoint 与 HITL | Document Review Agent | □ Code runs □ README updated □ Key concepts summarized □ Demo completed | 未开始
Week 7 - React Agent UI | 使用 React/Next.js 构建流式 Agent UI | Agent Frontend v1 | □ Code runs □ README updated □ Key concepts summarized □ Demo completed | 未开始
Week 8 - Security Analyst Agent | 整合 CVE、ATT&CK、IOC、报告生成与多 Agent | Security Analyst Agent v1 | □ Code runs □ README updated □ Key concepts summarized □ Demo completed | 未开始

## Resources
Category | Resource | Use in Plan | URL | Verification Note
Agent Foundation | Anthropic Building Effective Agents | Week 1 Day 1 | https://www.anthropic.com/research/building-effective-agents | Official resource
Agent Engineering | Anthropic Engineering | Week 1 Days 2-3 | https://www.anthropic.com/engineering | Official engineering hub
Agent SDK | OpenAI Agents SDK Docs | Weeks 1, 4, 8 | https://openai.github.io/openai-agents-python/ | Official documentation
Agent SDK | OpenAI Agents SDK GitHub | Week 4 | https://github.com/openai/openai-agents-python | Official repository
Claude API | Claude Academy | Week 2 | https://academy.claude.com/collections/build-with-claude | Official learning platform
MCP | Hugging Face MCP Course | Week 3 | https://huggingface.co/learn/mcp-course/unit0/introduction | International course
Vector Database | Qdrant Documentation | Week 5 | https://qdrant.tech/documentation/ | Official documentation
Orchestration | LangGraph Documentation | Weeks 6 and 8 | https://docs.langchain.com/oss/python/langgraph/overview | Official documentation
Frontend | React Learn | Week 7 | https://react.dev/learn | Official documentation
Frontend | Next.js Learn | Week 7 | https://nextjs.org/learn | Official course
Agent UI | Vercel AI SDK | Week 7 | https://sdk.vercel.ai/docs | Official documentation
Security | MITRE ATT&CK | Week 8 | https://attack.mitre.org/ | Official knowledge base
Security | NVD | Week 8 | https://nvd.nist.gov/ | Official NIST database